## Details
System | Item | Time (h)
RF | Logitudinal blowup in the faster ramp
RF | Capture with increased V at injection (5-6 MV) | 16
RF | 14 MV in physics (instead of 8 MV)
Damper | Setup for various beams
Injection | Inj sequencer stress test
Injection | Special SIS interlocks (inj osc. + interm. Intensity)
Injection | E-matching (f-b-f)
Injection | Abort and injection cleaning
Injection | Decay Q,Q' & b1 + correction
LBDS | Dumps in the ramp
MPS | FMCMs D1 @ 1.5 m
MPS | BLM dump test @ injection
MPS | FMCMs MSD
MPS | SMP SBF tables (ramp, 3.5 TeV)
MPS | BPF beam scraping tests
TOTEM/ALFA | RP alignment
Feedbacks | Dynamic reference
Feedbacks | Orbit/Q/Q' FB checks
Aperture | Global + IR 450 GeV
Aperture | 3.5 TeV?
Aperture | Injection prot
Xing/sep | Closure in squeeze?
Spectrometers | Test switching and build knobs?