## Slide 1: Status of 1m beta* commissioning
Jan Uythoven for the LHC team

## Slide 2: * = 1 m in IPs 1 and 5: The Context
During MD period optics with * = 1 m was tested using
  Tight collimator settings
  Reduced crossing angles from 120 rad to 100 rad
  Beam was unstable during squeeze
During same MD period the physical aperture around the triplets in the IPs was found to be larger than initially assumed
Decision in LMC last week
  Continue running with same collimator settings as before the TS
    TCTs IR1, 5 and 8 @ 11.8 
  Stay with the crossing angle of 120 rad
  Confirm the additional physical aperture
Start-up program after TS based on this

## Slide 3: Beam-beam separation
Beam-beam separation down below 6s for 100 mrad
  With 120 mrad ~ equivalent to nominal (b* 0.55 m)
W. Herr
Triplet
Triplet
To keep same separation with * = 1 m, need 140 mrad

## Slide 4: The commissioning blocks
Configuration:
  b* =1m, 120 mrad Xing angles.
  IR3+6+7 collimators at standard settings, TCTs 11.8s (IR1+5+8)
Block A: Aperture at 1m and 120 mrad
Block B: ALICE polarity reversal
Block C: Validation = loss maps
Block D: Intensity ramp up

## Slide 5: Block A : aperture check
Fill 1: 1 probe/beam, checkout cycle.
  b* 1 m and Xing angle 120 mrad.
  Standard collimator settings IR6+7.
  TCTs IR1/5 to be adapted to 120 mrad (setup on 100 mrad).
Fill 2: 2 nominals/beam, TCT alignment, orbit.
  TCTs IR1/5 alignment on 120 mrad, separated and in collision.
  Collision (re-)optimization with 120 mrad, reference orbit.
  End with loss map (H+V) and asynch dump. TCTs are 11.8s.
Fill 3: 1 probe/beam, aperture check @ 1 m.
  Repeat aperture measurement at 1 m.
  End with a loss map H, TCTs at 14s.
Fill 4: 1 probe/beam, aperture check with loss map.
  Loss map with TCTs at Xs, X = 13…14.
4h
6h
8h
5h
OK
OK, crossing plane separated beams missing* Q10-R1 ?
OK
* Crossing plane separated not required * Q10 – R1 confirmed as ‘noise’

## Slide 6: Block A: long range BB check
Fill 5: 84b with highly asymmetric BB filling pattern (also used for 1 m with 100 mrad).
  Bring the beam up to collisions.
  Verify stability and beam-beam effects.
6h
Trying again this afternoon

## Slide 7: Block B : ALICE polarity
Step 1: adjust injection, reference.
  ALICE on ‘old’ polarity.
  Injection steering with 12b, then copy to probe and check it.
Step 2: revert ALICE polarity.
  Check/correct orbit.
  Check/steer injection oscillations with probe, repeat with nominal.
Step 2’: re-steer TI2 if necessary.
  TDI coarse
  TL setup, TCDI alignment and verification.
Step 3: TDI/TCLI alignment.
  TDI/TCLI alignment with 1 nominal b.
  Check TDI,TCLI setup – check protection.
  Check injection 12b
2h
4h
12h
8h
OK
OK
OK

## Slide 8: Block B : ALICE polarity continued
Step 4: TCTs IR2 at injection.
  Setup TCTs in IR2 at injection.
Step 5: Checkout cycle, 2 probes/beam.
  Check Xing angle IR2 along the cycle.
  Correct orbit if necessary.
  TCTs IR2 ‘open’.
Step 6: TCT IR2 alignment cycle, 2 nominal b/beam.
  TCT alignment on flat top and in collision.
  Collision orbit, reference.
  Loss map H+V and asynch. dump.
(Step 7: TCT IR2 functions, positions and interlocks )
2h
4h
6h
OK
OK
Setting functions for the whole operational cycle were generated.
OK
OK

## Slide 9: Block C
Validations (loss maps, asynch dump checks) – to be confirmed with collimation team (Dp/p)
Finish coming night
Condition | Betatron H | Betatron V | Dp/p + | Dp/p - | Dump
Injection | DONE | REPEAT | DONE | DONE | OK
Flat top | DONE | DONE | --- | --- | REPEAT
Squeezed | DONE | DONE | --- | --- | DONE
Collisions | OK | X | X | OK | X

## Slide 10: Block D: Intensity ramp up
Proposed ramp up for stable beams:
  48b – short fill
  264 – short fill
  480 – short fill
  912 – long fill
  1380 – finally !!
Could go for stable beams this Wednesday

## Slide 11: Probing TCT – Triplet aperture
At the step of TCT gap between 14.8 and 15.3 sigmas, the losses move from the TCT to the MQX (light-orange line).
Corrector = aperture bump
BLM TCT
BLM triplet
TCT position

## Slide 12: Conclusions on Aperture so far
  Aperture confirmed at 1 m – there is enough aperture for *=1m & 120 µrad Xing angles, with around 2 sigma additional margin.
We can conclude that for the squeezed/separated case we found >16 sigmas in the separation plane. the crossing plane was only addressed in collision conditions.
IP1 (V): triplet at 14.8 -> 15.3 sigmas (collision and lumi scans IN) IP5 (H): triplet at 15.3 -> 15.8 sigmas (collision and lumi scans IN) IP1 (H): triplet at above 16.0 sigmas (squeezed, separated) IP5 (V): triplet at above 16.0 sigmas (squeezed, separated)
Betatron loss maps with TCTs at collision settings + 2sigma step out: Only small losses on the TCTs, and no losses on the triplets...
Loss maps show a peak in the Q10-R1. To be followed up.

## Slide 13: TDI alignment & angle set-up