## Schedule
Date | Day | Shift | Time (h) | Activity | Breakpoint | System/topic | Beam
0 |  |  | 8 | Ramp and squeeze checkout |  | Magnets | No beam
0 |  |  | 16 | TI2 and TI8 tests |  | Injection | Beam to TED
0 |  |  | 8 | BIS loop armed |  | BIS | No beam
0 |  |  | 8 | MKI/injection check |  | Injection | No beam
0 |  |  | 8 | Dump dry run |  | Dump | No beam
0 |  |  | 16 | RP interlock test (also modes) |  | MPS | No beam
1 | SA | M | 8 | Injection, first turn B1&B2 | First injections | OP | Probe
1 | SA | A | 8 | Closed orbit and capture B1&B2 |  | OP | Probe
1 | SA | N | 4 | Instrumentation - orbit, Q, Q', wire scanner |  | BI | Probe
1 | SA | N | 4 | Dispersion, CO, Q, Q',C- measure and correct |  | OP | Probe
2 | SU | M | 8 | RF capture and ADT first setup with probe |  | RF | Probe
2 | SU | A | 4 | Feedbacks - recommissioning at injection (Q, orbit, radial) |  | Feedback | Probe
2 | SU | A | 4 | Beta beating measurements and correction @ 450 GeV |  | Optics | Probe
2 | SU | N | 8 | Pre-cycle or ramp (no beam) - decay measurement at 450 GeV |  | Magnets | Probe
3 | MO | M | 8 | Ramp to 4 TeV - test QFB & OFB - test dump at 4 TeV | First ramp | Ramp | Probe
3 | MO | A | 8 | Squeeze to 0.6 m | First squeeze | Squeeze | Probe
3 | MO | N | 8 | Optics measurements / corrections in squeeze |  | Optics | Probe
4 | TUE | M | 8 | Reference orbit with probe |  | OP | Probe
4 | TUE | A | 8 | Injection correction and TI2/8 reference trajectories |  | Injection | Probe
4 | TUE | N | 8 | Pre-cycle or ramp (no beam) - decay measurement at 450 GeV |  | Magnets | Probe
5 | WED | M | 8 | Dump checkout |  | Dump | Probe
5 | WED | A | 8 | Dump checkout |  | Dump | Probe
5 | WED | N | 8 | BI shift |  | BI | Probe
6 | THU | M | 8 | Injection of nominal bunch |  | Injection | Nominal
6 | THU | A | 4 | Flat reference orbit at injection with nominal bunch | Nominal bunch | OP | Nominal
6 | THU | A | 4 | Damper setup for nominal bunch |  | ADT | Nominal
6 | THU | N | 8 | Squeeze to 0.6 m revisited - OFB and optics |  | Squeeze | Probe
7 | FRI | M | 8 | Orbit at injection with nominal bunch and bumps |  | OP | Nominal
7 | FRI | A | 4 | Experimental magnets ON |  | OP | Nominal
7 | FRI | A | 4 | Orbit feedback with dynamic reference in the ramp |  | Feedback | Nominal
7 | FRI | N | 8 | Aperture at injection | Aperture injection | Aperture | Probe
8 | SA | M | 8 | Dump checkout |  | Dump | Nominal
8 | SA | A | 8 | Dump checkout |  | Dump | Nominal
8 | SA | N | 8 | Pre-cycle or ramp (no beam) - decay measurement at 450 GeV |  | Magnets | Probe
9 | SU | M | 8 | Collimation setting-up 450 GeV | Collimation | Collimation | Nominal
9 | SU | A | 8 | RF and damper |  | RF | Nominal
9 | SU | N | 8 | Aperture at injection |  | Aperture | Probe
10 | MO | M | 8 | Collimation setting-up 450 GeV |  | Collimation | Nominal
10 | MO | A | 8 | TCDI setup |  | Injection | Nominal
10 | MO | N | 8 | Pre-cycle or ramp (no beam) - decay measurement at 450 GeV |  | Magnets | Probe
11 | TUE | M | 8 | BI shift |  | BI | Nominal
11 | TUE | A | 8 | Injection & dump protection 450 GeV |  | Injection | Nominal
11 | TUE | N | 8 | Loss maps and asynch dump tests at 450 GeV |  | Protection validation | Nominal
12 | WED | M | 8 | Injection protection validation |  | Protection validation | Probe
12 | WED | A | 8 | Squeeze to 0.6 m corrected |  | Squeeze | Probe
12 | WED | N | 8 | Aperture at 4 TeV squeezed - IR1/5 | Aperture 4 TeV | Aperture | Probe
13 | THU | M | 8 | Ramp, RF nominal bunch and longitudinal blowup |  | RF | Nominal
13 | THU | A | 8 | Collimation setup on flat top 4 TeV |  | Collimation | Nominal
13 | THU | N | 8 | MPS tests FMCMs |  | MPS | Probe
14 | FRI | M | 8 | Collimation setup on flat top 4 TeV |  | Collimation | Nominal
14 | FRI | A | 8 | BI shift |  | BI | Nominal
14 | FRI | N | 8 | Pre-cycle or ramp (no beam) - decay measurement at 450 GeV |  | Magnets | Nominal
15 | SAT | M | 8 | Multi-bunch injection 50 ns |  | Injection | 50 ns
15 | SAT | A | 8 | Transverse damper for multi-bunch 50 ns |  | ADT | 50 ns
15 | SAT | N | 8 | Aperture at 4 TeV squeezed - IR1/5 | Aperture 4 TeV | Aperture | Probe
16 | SUN | M | 8 | ADT : abort gap cleaning |  | ADT | Nominal
16 | SUN | A | 8 | Collimation / TCT setup squeezed |  | Collimation | Nominal
16 | SUN | N | 8 | Aperture at 4 TeV squeezed - IR2/8 |  | Aperture | Probe
17 | MO | M | 8 | Collimation / TCT setup squeezed |  | Collimation | Nominal
17 | MO | A | 8 | Multi-bunch injection 50 ns |  | Injection | 50 ns
17 | MO | N | 8 | BLM system checks |  | MPS | Nominal
18 | TUE | M | 8 | ADT : injection and abort gap cleaning |  | ADT | 50 ns
18 | TUE | A | 8 | BI shift |  | BI | 50 ns
18 | TUE | N | 8 | Aperture 4 TeV spare |  | Aperture
19 | WED | M | 8 | Pilot ramp & squeeze & collide , Q/Q' |  | Collisions | Nominal
19 | WED | A | 8 | Nominal bunch collisions |  | Collisions | Nominal
19 | WED | N | 8 | Spare
20 | THU | M | 8 | Collimation setup collisions |  | Collimation | Nominal
20 | THU | A | 8 | Collimation setup collisions |  | Collimation | Nominal
20 | THU | N | 8 | Loss maps and asynch dump 4 TeV |  | Protection validation | Nominal
21 | FRI | M | 8 | Loss maps and asynch dump 4 TeV |  | Protection validation | Nominal
21 | FRU | A | 8 | Loss maps and asynch dump 4 TeV |  | Protection validation | Nominal
21 | FRI | N | 8 | Loss maps and asynch dump 4 TeV |  | Protection validation | Nominal
22 | SAT | M | 8 | First stable beams, 3x3 | Stable Beams 3b | Collisions | Nominal
22 | SAT | A | 8 | Ramp squeeze collide 50 ns | Stable Beams 48b | Collisions | 50 ns

## Items
System | Item | Comment
ADT | Adjustments | 50 ns & signle b
ADT | Abort gap cleaning | To be made operational
ADT | Injection cleaning | Re-commission
ADT | Witness bunches for Q/Q'
RF | Cature etc tuning
RF | New longitudinal blowup
RF | Batch bowup | preperation
BI | Emittance devices
BI | OFB references | New system
BI | OFB gain and stability
BI | OFB bad BPM filter
BI | QFB | Re-commission
YASP | BPM quality | Commission
LBDS | TSU firmware
LBDS | AGK delay | Adjust
LBDS | No-dump trigger procedure | Test
LBDS | Beta* limits | Commission
Injection | TCDI automatic setup | Commission
SIS | Orbit & COD reference | Check
SIS | LSS6 BPM | Check
MPS | BPF limit | Check
MPS | FMCM D1 @ 0.6 m | Check
MPS | TOTEM & ALFA interlocks
Injectors | 3+3 injections PSB-PS

## Circuits
Name | Issue
RCO.A12B2 | Leakage current