## Slide 1: Technical Stop #4 29th August - 2nd September 2011
Summary of activities foreseen for the next TS
Julie Coupard
Schedule and Coordination

## Slide 2: Technical Infrastructure
Recurrent activities
  Maintenance
    Lift, access system, ventilation system, cooling system, cryogenics valves, UPS, handling system, lights, IT, alarm systems, power converters…
  Inspection
    Survey, water cooled cables, integration studies, X-rays, Radmon, collimators, civil engineering
  TIM test @Pt7
  Forward detector @Pt1 (ATLAS ZDC, ALFA) and @Pt5 (TOTEM)
  VIP visit @Pt5
In case of problem during the maintenance

## Slide 3: Technical Infrastructure
Special activities
  Lift
    PM25 - change of the speed limiter
  Cabling
    BLM @Pt3
    NG18 replacement @Pt3
    Thermo-switch @Pt1&2
    monitoring cryo @Pt4
  Optical Fibers Repair
  Cryogenics
    Modification of screw compressor @Pt6 on surface – should keep the cryo maintain
    Refurbishing of the QURCA @Pt8 as backup solution in case of problems with QURCB @Pt4
DSO Test on Friday 19:00
Intervention above/close to the machine

## Slide 4: Machine equipment
Beam instrumentation
    BRAN: Replace a BRANB preamp, Scintillator installation with surounding box in Pt1
    BWS: Investigate noise that came back on B1
    BGI: Camera remote control installation
    BLM: Direct beam dump connection to dump system
    BPM: New firmware and SW to increase IIR filter order, Modifs
    BTVM: Installation of a new acquisition system
    LDM: Replace B1 monitor with B2 type monitor
    BSRT: Move camera translation stage on both sides
    BCTDC: 24 bit board installation
    BBC: Visual inspection in IP1 and 5 of future location
    BBQ: Modifs

## Slide 5: Machine equipment
Kickers
    Maintenance and Tests @Pt2, 4, 6, 8
    Replacement of 2 entry boxes on MKBH tank @Pt6
    Change of generator pos K @Pt6
    Change of generator HV switch @Pt2
In case of problem during the maintenance

## Slide 6: Machine equipment
Machine Protection
    PLC moving @Pt1
    Upgrade of the DQAMC firmware for mitigation of SEU events
    Replacement of the power input switch on DQHDS Quench Heater Power Supplies
    Adjustment of 600 A Energy Extraction Switches
Vacuum
    Solenoide connection @Pt2
    Solenoide + thermo-switch @Pt5
    Sublimation of MKI @Pt2, 8
    X-rays @Pt7
Could create UFO ?
In case of problem during tests on Friday till 15:00

## Slide 7: Powering Tests
Circuit | Test | Current | Length | Constraints | UPS | DFB concerned | Patrol | CRYO OK | Lock | When
RCBCV9.R3B2 | R meas (MP3) |  |  | These tests will be done during the day with very low current and presence of people | P3 P4 |  | NO | A34 | NO | Mon???
RCBCH7.R3B1 | R meas (MP3) |  |  |  | P3 P4 |  | NO | A34 | NO | Mon???
RD3.R4 | ISRM meas (MP3) | ~3000 A | 2h | ElQA after PXI inst | P4 | DFBMK | P 4 5 6 | MR4 | NO | Wed
RD4.R4, RQ5.R4 | ISRM meas (MP3) | ~3000 A | 2h | ElQA after PXI inst | P4 | DFBML | P 4 5 6 | MR4 | NO | Wed
RQ6.R4 | ISRM meas (MP3) | ~3000 A | 2h | ElQA after PXI inst | P4 | DFBMG | P 4 5 6 | MR4 | NO | Thu
RB.A56 | Quench propagation test | I_nom | tbd | Powering phase II | P5 P6 | DFBAJ DFBAK | P4 P5 P6 | A56 | NO | Wed & Thu ???
RQD/F.A45 | Multiple FPA | see below | 6h | Powering phase II | P4 P5 | DFBAH DFBAI | P4 P5 P6 | A45 | NO | Thu
RU.L4 | Test on zero-offset reset | 400 A | 2h |  | P4 | DFBME | NO | ML4 | NO | Thu

## Slide 8: Special work hours
Optical fibers repair @Pt7
  Monday evening from 18:00 : intervention on optical fibers + LASS validation
  Friday evening from 19:00 : DSO Test
BLM cabling @Pt3
  Till 18:30 Tuesday
  07:30-18:30 Wednesday-Thursday
  From 07:30 Friday
Patrols
  07h30-9h30
  17h-19h

## Slide 9: Radio-Protection – New Safety Rules
TREC – Traceability of Radioactive Equipment at Cern
    https://espace.cern.ch/en-dep-mef-lpc/web%20pages/Traceability_SD1.pdf
  @Pt1
  @Pt2
DIMR – Demande d’Intervention en Milieu Radioactif
    https://espace.cern.ch/RP-LHC/Work%20planning/Forms/AllItems.aspx
  @Pt3
  @Pt7

## Slide 10: Thanks for your attention
Julie Coupard – on behalf of EN/MEF-LPC team