## Slide 1: Technical Stop #1 2012
Summary of activities
Julie Coupard
Schedule and Coordination

## Slide 2
Activity | Title | Responsible |  | Status
16172 | Replace sensor on MQXB.B2R2.B | ANDREAS HERTY | BE-ABP-SU | Approved
16641 | Check force sensor cables (IP8) | ANTONIO MARIN | BE-ABP-SU | Approved
16640 | Check force sensor cables (IP2) | ANTONIO MARIN | BE-ABP-SU | Approved
16639 | Check force sensor cables (IP1) | ANTONIO MARIN | BE-ABP-SU | Approved
17356 | Inspection visit (IP1) | HELENE MAINAUD DURAND | BE-ABP-SU | Approved
16651 | Calage des points photos google Point_8 | MONIQUE TORTRAT | BE-ABP-SU | In progress
16482 | Calage des points photos google Point_1 | MONIQUE TORTRAT | BE-ABP-SU | In progress
16652 | Calage des points photos google Point_2 | MONIQUE TORTRAT | BE-ABP-SU | In progress
16174 | Installation of force sensors | MATEUSZ PAWEL SOSIN | BE-ABP-SU | In progress
16918 | Polygonale de rattachement - Point 5 | MICHEL TROILLET | BE-ABP-SU | Approved
16390 | Polygonation PT8 | JEAN-FREDERIC FUCHS | BE-ABP-SU | In progress
16380 | Mesure_3 Low Beta 2L | JEAN-FREDERIC FUCHS | BE-ABP-SU | Approved
16379 | Mesure_2 Low Beta 5L | JEAN-FREDERIC FUCHS | BE-ABP-SU | Approved
16370 | Mesure_1 Low Beta 8R et 8L | JEAN-FREDERIC FUCHS | BE-ABP-SU | Approved
16385 | Mesure plani C20L8M | JEAN-FREDERIC FUCHS | BE-ABP-SU | In progress

## Slide 3
Activity | Title | Responsible |  | Status
17333 | LHC BGI maintenance | MARIUSZ GRACJAN SAPINSKI | BE-BI-BL | In progress
16219 | BI-BLM:LIC installation for sunglasses | EWALD EFFINGER | BE-BI-BL | Approved
17120 | Checking the internet connection of the PS for BLMD | EWALD EFFINGER | BE-BI-BL | Late
16220 | BI-BLM:LIC replacement | EWALD EFFINGER | BE-BI-BL | In progress
17121 | Connecting the PS for BLMD in UJ 33 | EWALD EFFINGER | BE-BI-BL | In progress
17119 | Installation BLMD equipment in USC55 and cell 4 left and right. | EWALD EFFINGER | BE-BI-BL | Late
17114 | Replacing of control electronic in UA87 | EWALD EFFINGER | BE-BI-BL | Late
17115 | Checking the installed LICs | EWALD EFFINGER | BE-BI-BL | Late
17106 | Replacing of 6 SEMs by 6 LICs in A6L2 | EWALD EFFINGER | BE-BI-BL | Late
17326 | Checking the position of the BLMD installation cell 4 left and right. | EWALD EFFINGER | BE-BI-BL | In progress
17117 | Exchange for 3 prototype LICs in LSS7 | EWALD EFFINGER | BE-BI-BL | Late
17116 | Installation of the scope in UA87 for BLMD | EWALD EFFINGER | BE-BI-BL | Late
16662 | change of all DABs on CFV-UA47-BCTFRC | DAVID BELOHRAD | BE-BI-PI | In progress
16839 | Moving Didt box on system A | MATHIAS PFAUWADEL | BE-BI-PI | In progress
17302 | Power supply issue on BRAN IP8 Left | ENRICO BRAVIN | BE-BI-PM | Approved
17131 | BSRT Technical Stop | FEDERICO RONCAROLO | BE-BI-PM | In progress
17004 | LDM troubleshooting | ADAM JEFF | BE-BI-PM | In progress

## Slide 4
Activity | Title | Responsible |  | Status
17250 | Changement FIP repeater Cryo | JULIEN PALLUEL | BE-CO-FE | Late
Activity | Title | Responsible |  | Status
17343 | LLRF maintenance/upgrade | PHILIPPE BAUDRENGHIEN | BE-RF-FB | In progress
16476 | ACS TS1, restart and powering test | PIERRE MAESEN | BE-RF-KCA | In progress
16350 | Maintenance et modification sur installation RF ADT et cavite ACS | GINO CIPOLLA | BE-RF-PM | In progress
Activity | Title | Responsible |  | Status
17084 | Suivi radioprotection TS1-2012 | CHRISTOPHE TROMEL | DGS-RP-AS | In progress
17150 | Suivi radioprotection | CHRISTOPHE TROMEL | DGS-RP-AS | In progress
17177 | RAMSES - LH7 - DA Upgrade | ALASDAIR DAY | DGS-RP-IL | Approved
17323 | RAMSES - LHC1 - PHFL1591 corrective action | ALASDAIR DAY | DGS-RP-IL | Approved
17181 | RAMSES - LH4 - DA Upgrade | ALASDAIR DAY | DGS-RP-IL | Approved
17263 | RAMSES - LHC4 - Reparation PCM 4591 | GAEL DUCOS | DGS-RP-IL | In progress
17148 | Coordination LHC | ENRICO CENNINI | DGS-SEE | In progress
17154 | Réception équipement de levage | LAURENT COLLY | DGSSEESIS | In progress

## Slide 5
Activity | Title | Responsible |  | Status
16273 | Replacement of rising pump cubicle | ANDERS KJAER ANDERSEN | EN-CV-DOW | In progress
16681 | visite etancheite sur groupes froid Trane | FORTUNATO CANDITO | EN-CV-DOW | In progress
16718 | travaux LS1 | MAGALI MENDEZ | EN-CV-MA | In progress
16294 | Réparations et graissage sur les tours du point 8 | GILLES YVES MORARD | EN-CV-OP | In progress
16292 | Inspection, tournée de vérification, correctifs en UW85 | GILLES YVES MORARD | EN-CV-OP | In progress
16319 | controle station refroidissement cryo | DOMINIQUE PIEDNOIR | EN-CV-OP | Late
16293 | Réparations d'une fuite au SD2 | DOMINIQUE PIEDNOIR | EN-CV-OP | Late
16289 | Inspection, tournée de vérification, correctifs en UW25 | DOMINIQUE PIEDNOIR | EN-CV-OP | In progress
16284 | Vérification des filtres sur les cables refroidis et convertisseurs ventilation en souterrain au point 2 | DOMINIQUE PIEDNOIR | EN-CV-OP | In progress
16286 | Réparations et graissage sur les tours du point 2 | DOMINIQUE PIEDNOIR | EN-CV-OP | In progress
16280 | Maintenance ventilation en souterrain au point 2 | DOMINIQUE PIEDNOIR | EN-CV-OP | In progress
16288 | Réparations et graissage sur les tours du point 4 | FREDERIC LOUIS JUBAN | EN-CV-OP | In progress
17251 | changement carte de communication | FREDERIC LOUIS JUBAN | EN-CV-OP | Late
16290 | Inspection, tournée de vérification, correctifs en UW45 | FREDERIC LOUIS JUBAN | EN-CV-OP | In progress
17322 | prelevement eau de relevage | FREDERIC LOUIS JUBAN | EN-CV-OP | Approved
16815 | chgt pressostat sf5 | GILLES DUCRET | EN-CV-OP | Late
16910 | Inspection, tournée de vérification, pompe eau brute UJ56 | GILLES DUCRET | EN-CV-OP | In progress
16295 | Remplacement d'un détendeur sur la ventilation en RR53 | VINCENT PITTIN | EN-CV-OP | In progress
16291 | Inspection, tournée de vérification, correctifs en UW65 | VINCENT PITTIN | EN-CV-OP | In progress
16281 | Maintenance ventilation en souterrain au point 6 | VINCENT PITTIN | EN-CV-OP | In progress
17001 | Pompage fosse eau claire UJ76 | VINCENT PITTIN | EN-CV-OP | Approved
17000 | Verification ventilation | VINCENT PITTIN | EN-CV-OP | Approved
16520 | UX65 : Maintenance fosses | VINCENT PITTIN | EN-CV-OP | In progress
16345 | Replace fosse level transmitter TNM41 | WILLIAM THOMAS BANNISTER | EN-CV-OP | Approved
16073 | Maintenance cooling eau mixte US15 | DENIS DUMAS | EN-CV-OP | Late
17143 | R2E preparation | PIERO VALENTE | EN-CV-PJ | In progress

## Slide 6
Activity | Title | Responsible |  | Status
16572 | UJ33 - Remplacement câble EBD129/33 | THIERRY BOURREL | EN-EL-BT | In progress
16503 | Supervision travaux EL | JEROME PIERLOT | EN-EL-BT | In progress
16502 | Supervision travaux EL | JEROME PIERLOT | EN-EL-BT | In progress
16501 | Supervision travaux EL | JEROME PIERLOT | EN-EL-BT | In progress
16500 | Supervision travaux EL | JEROME PIERLOT | EN-EL-BT | In progress
16506 | Supervision travaux EL | JEROME PIERLOT | EN-EL-BT | In progress
16505 | Supervision travaux EL | JEROME PIERLOT | EN-EL-BT | In progress
16504 | Supervision travaux EL | JEROME PIERLOT | EN-EL-BT | In progress
16499 | Supervision travaux EL | JEROME PIERLOT | EN-EL-BT | In progress
16919 | UA63 - Installation réglette prises dans rack MYDGP07 | VINCENT RAYMOND CHAREYRE | EN-EL-BT | In progress
16932 | UA67 - Installation réglette prises dans rack MYDGP07 | VINCENT RAYMOND CHAREYRE | EN-EL-BT | In progress
16532 | Remplacement ecl. sécu arc 1-2 | STEPHANE DELARUE | EN-EL-BT | In progress
17130 | Remplacement ecl. sécu arc 1-8 | STEPHANE DELARUE | EN-EL-BT | Approved
17129 | Remplacement ecl. sécu | STEPHANE DELARUE | EN-EL-BT | Late
16542 | TABLEAUX FIXES (INSPECTION DE SECURITE | STEPHANE DELARUE | EN-EL-BT | In progress
16541 | Remplacement batterie UPS | STEPHANE DELARUE | EN-EL-BT | Approved
16259 | MAINTENANCE UPS ESS11/25 EN UW25 | BRUNO ALAIN SOLLIER | EN-EL-BT | Approved
16537 | MAINTENANCE EZS11/45X EN UX45 (DEPANNAGE | BRUNO ALAIN SOLLIER | EN-EL-BT | In progress
16257 | MAINTENANCE EBS11/28 EN RE28 | BRUNO ALAIN SOLLIER | EN-EL-BT | Approved

## Slide 7
Activity | Title | Responsible |  | Status
16585 | Reprise des connecteurs capteur de force au pt2 | CHRISTOPHE LEON JANOWICZ | EN-EL-CF | In progress
16339 | Préparation et suivi des travaux pt8 | CHRISTOPHE LEON JANOWICZ | EN-EL-CF | In progress
16338 | Préparation et suivi des travaux pt7 | CHRISTOPHE LEON JANOWICZ | EN-EL-CF | In progress
16335 | Préparation et suivi des travaux pt4 | CHRISTOPHE LEON JANOWICZ | EN-EL-CF | In progress
16334 | Préparation et suivi des travaux pt3 | CHRISTOPHE LEON JANOWICZ | EN-EL-CF | In progress
16337 | Préparation et suivi des travaux pt6 | CHRISTOPHE LEON JANOWICZ | EN-EL-CF | In progress
16333 | Préparation et suivi des travaux pt2 | CHRISTOPHE LEON JANOWICZ | EN-EL-CF | In progress
16330 | Préparation et suivi des travaux pt1 | CHRISTOPHE LEON JANOWICZ | EN-EL-CF | In progress
16595 | Câblage beam interlocks en UA87 | CHRISTOPHE LEON JANOWICZ | EN-EL-CF | Approved
16593 | Câblage beam interlocks en UA23 | CHRISTOPHE LEON JANOWICZ | EN-EL-CF | In progress
16592 | Raccordement câblage thermoswitchs en UA87 | CHRISTOPHE LEON JANOWICZ | EN-EL-CF | In progress
16588 | Reprise des connecteurs capteur de force au pt5 | CHRISTOPHE LEON JANOWICZ | EN-EL-CF | In progress
16336 | Préparation et suivi des travaux pt5 | CHRISTOPHE LEON JANOWICZ | EN-EL-CF | In progress
16591 | Raccordement câblage thermoswitchs en RR77 | CHRISTOPHE LEON JANOWICZ | EN-EL-CF | In progress
16579 | Reprise des connecteurs capteur de force au pt1 | CHRISTOPHE LEON JANOWICZ | EN-EL-CF | In progress
16873 | Optical fibre installation UJ56 - R532 | ANTONIO GONZALEZ PUERTAS | EN-EL-CF | In progress
16903 | Optical fibre measurements and inspection P8 | ANTONIO GONZALEZ PUERTAS | EN-EL-CF | In progress
16899 | Optical fibre measurements and inspection P6 | ANTONIO GONZALEZ PUERTAS | EN-EL-CF | In progress
16894 | Optical fibre measurements and inspection P5 | ANTONIO GONZALEZ PUERTAS | EN-EL-CF | In progress
16892 | Optical fibre measurements and inspection P3 | ANTONIO GONZALEZ PUERTAS | EN-EL-CF | In progress
16885 | Optical fibre measurements and inspection P1 | ANTONIO GONZALEZ PUERTAS | EN-EL-CF | In progress
16884 | Optical fibre tube reparation RE72 | ANTONIO GONZALEZ PUERTAS | EN-EL-CF | In progress
16876 | Optical fibre installation UJ56 - R571 | ANTONIO GONZALEZ PUERTAS | EN-EL-CF | In progress
16872 | Optical fibre installation RA43-US45 Matching monitors | ANTONIO GONZALEZ PUERTAS | EN-EL-CF | In progress
16901 | Optical fibre measurements and inspection P7 | ANTONIO GONZALEZ PUERTAS | EN-EL-CF | In progress
16893 | Optical fibre measurements and inspection P4 | ANTONIO GONZALEZ PUERTAS | EN-EL-CF | In progress
16890 | Optical fibre measurements and inspection P2 | ANTONIO GONZALEZ PUERTAS | EN-EL-CF | In progress
16871 | Optical fibre installation RA47-US45 | ANTONIO GONZALEZ PUERTAS | EN-EL-CF | In progress
16826 | Optical fibre installation RA43-US45 | ANTONIO GONZALEZ PUERTAS | EN-EL-CF | In progress

## Slide 8
Activity | Title | Responsible |  | Status
16408 | Remplacement cable controle EBD129/33 | LAURENT RANDOT | EN-EL-CO | In progress
16222 | Inspection visuel de cable 18kV | SERGE CHALAYE | EN-EL-HT | In progress
16633 | Piquet electrique | GERARD CUMER | EN-EL-OP | In progress
16914 | investigation cellule 18KV HT LHC6 | DAVID ROBERT DI LAZZARO | EN-EL-OP | Approved

## Slide 9
Activity | Title | Responsible |  | Status
17341 | Consigantion Monorail | ANTONIO FORESTE | EN-HE-AW | In progress
16691 | ACTIVITES MANUTENTIONS TS1 (AVRIL 2012 | SERGE PELLETIER | EN-HE-HH | In progress
16799 | Visite sur site pour photos et mesures | SERGE PELLETIER | EN-HE-HH | In progress
17241 | Realisation travaux palans US15 | DAMIEN LAFARGE | EN-HE-HM | In progress
17243 | Reception travaux palans US45 | DAMIEN LAFARGE | EN-HE-HM | In progress
17244 | Reception travaux palans US25 | DAMIEN LAFARGE | EN-HE-HM | In progress
17237 | Contrôle étanchéité ponts roulants | DAMIEN LAFARGE | EN-HE-HM | Late
17238 | Travaux sur porte puits SD4/US45 | DAMIEN LAFARGE | EN-HE-HM | In progress
17242 | Reception travaux palans US65 | DAMIEN LAFARGE | EN-HE-HM | In progress
16526 | Réparation câble pont suite AR n°10326 | DAMIEN LAFARGE | EN-HE-HM | In progress
16818 | Inspection collimateur point 7 | THIERRY FENIET | EN-HE-HT | Approved
17297 | Inspection collimateur point 3 | THIERRY FENIET | EN-HE-HT | In progress
16814 | Inspection collimateur point 3 | THIERRY FENIET | EN-HE-HT | Late
17139 | PM15 LIFT PHOTOS | NICOLAS PEREZ | EN-HE-LM | Late
16571 | PM32 APRIL LIFT MAINTENANCE | NICOLAS PEREZ | EN-HE-LM | Approved
16568 | PM25 APRIL LIFT MAINTENANCE | NICOLAS PEREZ | EN-HE-LM | In progress
16569 | PZ33 APRIL LIFT MAINTENANCE | NICOLAS PEREZ | EN-HE-LM | Approved
16557 | PM15 APRIL LIFT MAINTENANCE | NICOLAS PEREZ | EN-HE-LM | Late
16589 | PM85 APRIL LIFT MAINTENANCE | NICOLAS PEREZ | EN-HE-LM | Approved
16584 | PM65 APRIL LIFT MAINTENANCE | NICOLAS PEREZ | EN-HE-LM | Approved
16582 | PM45 APRIL LIFT MAINTENANCE | NICOLAS PEREZ | EN-HE-LM | Approved
16581 | PZ45 APRIL LIFT MAINTENANCE | NICOLAS PEREZ | EN-HE-LM | Late
16566 | PM18 APRIL LIFT MAINTENANCE | NICOLAS PEREZ | EN-HE-LM | Approved
16587 | PM76 APRIL LIFT MAINTENANCE | NICOLAS PEREZ | EN-HE-LM | Approved
16586 | PZ65 APRIL LIFT MAINTENANCE | NICOLAS PEREZ | EN-HE-LM | Approved
16583 | PM56 APRIL LIFT MAINTENANCE | NICOLAS PEREZ | EN-HE-LM | Late
15962 | [Piquet] LHC Lift Troubleshooting | ANTONINO CALDERONE | EN-HE-LM | In progress

## Slide 10
Activity | Title | Responsible |  | Status
17245 | Réfection toilettes US | SERGE GRILLOT | EN-MEF-COL | In progress
17233 | Viste integration | YVON MUTTONI | EN-MEF-INT | Approved
16994 | Visite Inspection Installation | FREDERIC GALLEAZZI | EN-MEF-INT | Approved
16445 | ALFA - Upgrades | ANNE-LAURE PERROT | EN-MEF-LE | In progress
16453 | CMS FSC - Upgrades | ANNE-LAURE PERROT | EN-MEF-LE | In progress
16930 | R2E and Forward detectors -visits | ANNE-LAURE PERROT | EN-MEF-LE | In progress
16456 | CMS ZDC - Installation | ANNE-LAURE PERROT | EN-MEF-LE | In progress
16913 | ALICE ZDC - Maintenance and checks | ANNE-LAURE PERROT | EN-MEF-LE | In progress
16451 | TOTEM - Maintenance and checks | ANNE-LAURE PERROT | EN-MEF-LE | In progress
16440 | ATLAS ZDC - Installation | ANNE-LAURE PERROT | EN-MEF-LE | In progress
17362 | TEST k | KATY KARINE FORAZ | EN-MEF-OSS | In progress
17360 | TEST k | KATY KARINE FORAZ | EN-MEF-OSS | Approved
17146 | Coordination LHC | KATY KARINE FORAZ | EN-MEF-OSS | In progress
16955 | Visite pour installation passerelle d'acces Cryo | EMMANUEL PAULAT | EN-MEF-OSS | In progress
16693 | viiste profesionnelle | MICHEL ARNAUD | EN-MEF-OSS | Approved
16606 | visite pour adéquation échafaudages | GIANLUCA CANALE | EN-MEF-SI | Approved
16549 | installation échafaudage TZ 76 point 7 | GIANLUCA CANALE | EN-MEF-SI | Approved

## Slide 11
Activity | Title | Responsible |  | Status
16567 | Collimators - Repair TCSG.5L3.B1 | JEROME LENDARO | EN-STI-ECE | In progress
16560 | Collimators - Inspection and Maintenance | JEROME LENDARO | EN-STI-ECE | Approved
16561 | Collimators - control system data acquisiiton | JEROME LENDARO | EN-STI-ECE | In progress
16565 | RADMONs - Inspection and Maintenance | JEROME LENDARO | EN-STI-ECE | In progress
17334 | R2E inspections on equipment P4 and P6 | MARCO CALVIANI | EN-STI-EET | Approved
17039 | TLD retrieval | PETRA MALA | EN-STI-EET | Late

## Slide 12
Activity | Title | Responsible |  | Status
16980 | Maintenance PAD/MAD UJ16 | TONO RIESCO HERNANDEZ | GS-ASE-AC | Approved
16973 | Maintenance PAD PM85 | TONO RIESCO HERNANDEZ | GS-ASE-AC | In progress
16968 | Maintenance PAD/MAD PM85 | TONO RIESCO HERNANDEZ | GS-ASE-AC | Late
16982 | Installation Nouvelle Bio PZ33 | TONO RIESCO HERNANDEZ | GS-ASE-AC | Late
16920 | Piquet Access ZORA | TONO RIESCO HERNANDEZ | GS-ASE-AC | In progress
16992 | Installation Nouvelle Bio PM25 | TONO RIESCO HERNANDEZ | GS-ASE-AC | Approved
16984 | Installation Nouvelle Bio PM15 | TONO RIESCO HERNANDEZ | GS-ASE-AC | Approved
16983 | Installation Nouvelle Bio PM18 | TONO RIESCO HERNANDEZ | GS-ASE-AC | In progress
16981 | Maintenance PAD/MAD UJ87 | TONO RIESCO HERNANDEZ | GS-ASE-AC | Approved
16976 | Maintenance PAD/MAD UJ83 | TONO RIESCO HERNANDEZ | GS-ASE-AC | Approved
16765 | SFDIN-00294 Maintenance trimestrielle secteur 2 | DENIS RAFFOURT | GS-ASE-AS | In progress
16719 | Test alarmes détection incendie secteur 1 | DENIS RAFFOURT | GS-ASE-AS | Approved
16773 | SFDIN-00295 Maintenance trimestrielle secteur 3 | DENIS RAFFOURT | GS-ASE-AS | Approved
16772 | SESEV-00102 Modification alimentation sirènes secteur 3 | DENIS RAFFOURT | GS-ASE-AS | In progress
16732 | SFDIN-00296 Maintenance trimestrielle secteur 4 | DENIS RAFFOURT | GS-ASE-AS | In progress
16735 | Réception HSE Détection incendie UX25 | DENIS RAFFOURT | GS-ASE-AS | Late
16733 | SFDIN-00292 Maintenance trimestrielle secteur 6 | DENIS RAFFOURT | GS-ASE-AS | In progress
16614 | SGGAZ-00148 Maintenance trimestrielle secteur 5 | NICOLAS MICHEL BROCA | GS-ASE-AS | Approved
16610 | SGGAZ-00152 Maintenance trimestrielle secteur 7 | NICOLAS MICHEL BROCA | GS-ASE-AS | Approved
16628 | Visite UJ76 cote tunnel | NICOLAS MICHEL BROCA | GS-ASE-AS | In progress
16626 | Réception par HSE détection ODH portes saloon secteur 5 | NICOLAS MICHEL BROCA | GS-ASE-AS | Approved
16616 | Modification sur 2 détecteurs ODH en UJ76 | NICOLAS MICHEL BROCA | GS-ASE-AS | Approved
16615 | SGGAZ-00146 Maintenance trimestrielle secteur 3 | NICOLAS MICHEL BROCA | GS-ASE-AS | Approved
16613 | SGGAZ-00147 Maintenance trimestrielle secteur 4 | NICOLAS MICHEL BROCA | GS-ASE-AS | Approved
16609 | SGGAZ-00154 Maintenance trimestrielle secteur 1 | NICOLAS MICHEL BROCA | GS-ASE-AS | Approved
17147 | Coordination LHC | MAURICI GALOFRE VILA | GS-FB | In progress
17280 | Nettoyage toilettes en US | ALAIN BERTRAND | GS-IS-SIS | In progress
16821 | Visit TZ76 for CE estimate | JUNY CRESPO BISQUERT | GS-SE-CEP | Approved
17182 | Echelle | DANIEL PARCHET | GS-SE-CEP | In progress

## Slide 13
Activity | Title | Responsible |  | Status
16328 | Visite d'inspection pour le wifi | LESZEK ADAM BORAKIEWICZ | IT-CS-CD | In progress
16329 | Visite d'inspection du réseau informatique | STEPHANE CASENOVE | IT-CS-CD | In progress
16434 | Pose et mise en service d'un switch 3COM 4400 (TN en UJ33 | MOHSSEN SOUAYAH | IT-CS-CD | Approved
17038 | Piquet Firstline reseau | JEAN-PIERRE PUGET | IT-CS-CS | In progress
17044 | test UMTS dans les bat SD8 et RE12 | FREDERIC CHAPRON | IT-CS-CS | In progress
Activity | Title | Responsible |  | Status
17311 | Check fiber bundle routing for ZDC | SERGEI MALYUKOV | PH-ADO | Approved
17357 | Verification N2 pour aimant l3 | PHILIPPE JACQUES BOUVIER | PH-DT-EM1 | In progress
17347 | Verification N2 pour aimant l3 | PHILIPPE JACQUES BOUVIER | PH-DT-EM1 | In progress
16923 | LV power supply replacement | PETR SICHO | PH-UAT | Late
17158 | ATLAS IDE Intervention | KOICHI NAGAI | PH-UAT | In progress

## Slide 14
Activity | Title | Responsible |  | Status
17144 | QU (CRYO UNDERGROUND Instrumentation CRYO TUNNEL - TS#1 2012 | JUAN CASAS-CUBILLOS | TE-CRG-CI | In progress
17155 | QU (CRYO UNDERGROUND Préparation LS1 - CRYO TUNNEL - TS#1 2012 | OLIVIER PIROTTE | TE-CRG-ME | In progress
17103 | QU (CRYO UNDERGROUND Maintenance CRYOPLANTS en CAVERNES - TS#1 2012 2011 | GORAN PERINIC | TE-CRG-ML | In progress
17179 | QU (CRYO UNDERGROUND Rondes Cryo Tous Sites - TS#1 2012 | SERGE CLAUDET | TE-CRG-OA | In progress
Activity | Title | Responsible |  | Status
16518 | Connection MKI fast interlock to Injection BIC | ETIENNE CARLIER | TE-ABT-EC | In progress
16516 | Electronics & Controls support for MKD generators exchange | ETIENNE CARLIER | TE-ABT-EC | In progress
16522 | LBDS maintenance activities | ETIENNE CARLIER | TE-ABT-EC | In progress
17135 | TCDQ B1 & B2 - CONTROL MOTORS CLUTCH | CHRISTOPHE BOUCLY | TE-ABT-EC | In progress
17285 | Test HT et validation LBDS | VILIAM SENAJ | TE-ABT-FPS | In progress
16683 | Inspection du contact életrique sur 3 MKD | FRANCESCO CASTRONUOVO | TE-ABT-FPS | In progress
16519 | Remplacement de 2 Générateurs MKD | FRANCESCO CASTRONUOVO | TE-ABT-FPS | Late
17286 | Visite d'inspection tanks MKI PT2/Pt8 | MICHAEL JOHN BARNES | TE-ABT-FPS | In progress
16517 | Maintenance sur générateurs MKI | MICHAEL JOHN BARNES | TE-ABT-FPS | In progress

## Slide 15
Activity | Title | Responsible |  | Status
16466 | EPC - Maintenance of LHC Power Converters | VALERIE MONTABONNET | TE-EPC-OMS | In progress
16461 | EPC - Locking/Unlocking of LHC Power Converters | VALERIE MONTABONNET | TE-EPC-OMS | In progress
Activity | Title | Responsible |  | Status
16902 | RCO.A78.B2: Splice issue | GIORGIO D'ANGELO | TE-MPE-EE | In progress
16898 | RCOSX3.L1: circuit opened | GIORGIO D'ANGELO | TE-MPE-EE | In progress
Activity | Title | Responsible |  | Status
16022 | 3G data connection test | ANDREA MUSSO | TE-MSC-CMI | Approved

## Slide 16
Activity | Title | Responsible |  | Status
17053 | [Piquet] Vacuum | LUDOVIC MOURIER | TE-VSC-EIV | In progress
15998 | Depannage groupe de pompages | LUDOVIC MOURIER | TE-VSC-EIV | Late
17055 | remplacement préventif pompes turbo arc | LUDOVIC MOURIER | TE-VSC-EIV | In progress
17056 | remplacement préventif pompes primaire | LUDOVIC MOURIER | TE-VSC-EIV | In progress
17007 | calibration et QA | GAEL CLAUDE JOEL GIRARDOT | TE-VSC-ICM | In progress
17013 | BGI | GAEL CLAUDE JOEL GIRARDOT | TE-VSC-ICM | In progress
17010 | etiquetage equipements vide isolation | GAEL CLAUDE JOEL GIRARDOT | TE-VSC-ICM | In progress
17005 | boitiers profibus | GAEL CLAUDE JOEL GIRARDOT | TE-VSC-ICM | In progress
17178 | TS1_2012_A238 visit LSS7 preparation LS1 | GREGORY CATTENOZ | TE-VSC-LBV | In progress
17174 | TS1_2012_A237 visit LSS3 preparation LS1 | GREGORY CATTENOZ | TE-VSC-LBV | Approved
16852 | Tirs radiologiques LSS | ALEXIS VIDAL | TE-VSC-LBV | In progress
16634 | TS01-2012, LSS2 L MKI/TDI etuvage | NICOLAS ZELKO | TE-VSC-LBV | In progress
16636 | TS01-2012, LSS8 R MKI/TDI etuvage | NICOLAS ZELKO | TE-VSC-LBV | In progress
17186 | TS01-2012, LSS3 Installation of new VHLXZ | JULIEN FINELLE | TE-VSC-LBV | Approved
16625 | installation nouveau support au point 3 | JULIEN FINELLE | TE-VSC-LBV | Late
16623 | Inspection LSS6 | JULIEN FINELLE | TE-VSC-LBV | Late

## Slide 17: Thanks for your attention
Julie Coupard – on behalf of EN/MEF-OSS team