## Slide 1
Scrubbing run plan
G. Arduini with input from: V. Baglin, S. Claudet, J.-M. Jimenez, E. Métral, G. Rumolo, L. Tavian, F. Zimmermann

## Slide 2: Aims of the scrubbing run
Reduction of the SEY in the arcs and straight sections to allow for operation with 75 and possibly 50 ns beams with acceptable heat load and vacuum pressure rise and acceptable blow-up
Allow fast ramp-up with 75 or possibly 50 ns beams up to 900 – 1400 bunches in steps of 100-200 bunches per step (see Chamonix)
To be noted:
  The 50 ns beam has an higher potential in terms of bunch population in the injectors
As a by-product:
  Allow early detection of issues for high intensity operation (RF, UFOs, etc.)

## Slide 3: Scrubbing run requirements
Requirements for the scrubbing run:
  In the injectors:
    50 ns beam with up to 1.5x1011 p/bunch with emittances in the range 2-3.5 mm (single and double batch injection)
    25 ns beam with 1.15x1011 p/bunch with nominal emittance
During the scrubbing run:
    Solenoids (experimental and anti e-cloud) and experimental dipoles should be OFF
    Vacuum interlock levels should be temporarily increased to 1x10-6 mbar (from 4x10-7 mbar) where and if needed and compatibly with machine and experiment protection requirements
    Cryo valve regulation for the beam screen in the arcs set to 25 K for the cells used for heat load reference measurements

## Slide 4: Preparation
  Heat load calibration for a few cells (including one with inverted beam screens in Sector 34)  3-4 hours with no powering and no beam at the end of the technical stop on Thursday
  Injection of up to 96 bunches with 75 ns spacing (as intermediate step to prepare injection of 50 ns beam injection)
  Injection of up to 144 bunches with 50 ns spacing
  If significant pressure rises during the setting-up of injection  interleave setting-up with scrubbing to allow next step in injection. Increase of the vacuum interlock level might be required already in this phase in some locations.

## Slide 5: Day 1-3
Inject trains of up to 4x36 bunches (>1.3x1011 p/b) with 50 ns spacing with nominal emittance up to >1000 bunches compatibly with vacuum rise, heat loads and beam stability:
  Injection of trains of 36 bunches from the SPS and nominal spacing in the LHC (975 ns – i.e. 38 empty 25 ns slots)
    Monitoring of the temperature of the beam screens and RF stable phase (µ energy loss) as well as vacuum evolution to follow-up the scrubbing progress
  Once filled the whole machine dump and go to the next step: injection of nx36 bunches from SPS and nominal spacing in the LHC (n=2,3,4)
  Try and reduce bunch-length or the transverse emittance of the beam to enhance scrubbing.

## Slide 6: Day 4
Evaluation of the sensitivity to orbit distortion and radial position at 450 GeV/c
  Introduce a peak-to-peak orbit distortion of ±1 mm
  Introduce a radial position error of ±1×10-3
Ramp/squeeze/collision with 50 ns beams (number of bunches as achieved with 75 ns). For the ramp vacuum interlock levels will be restored to nominal settings. Preceded by test ramp. Requires check of LSS6 BPMs
Reduce separation bumps and crossing angles with one beam to check sensitivity to local orbit

## Slide 7: Day 5-7
Inject trains of 4x36 bunches (>1.3x1011 p/b) with 50 ns spacing with small transverse emittance
if saturation in the scrubbing with 50 ns beams inject up to 2x72 bunches (1.1-1.2x1011 p/b) with 25 ns spacing with nominal emittance up to ~2000 bunches compatibly with vacuum rise, heat loads and beam stability:
  Injection of 25 ns beams (same number of bunches as 50 ns, same user in SPS) will require 1-3 shifts of injection set-up
  Injection of trains of 72 bunches from the SPS and nominal spacing in the LHC (975 ns – i.e. 38 empty 25 ns slots)
    Monitoring of the temperature of the beam screens and RF stable phase (µ energy loss) as well as vacuum evolution to follow-up the scrubbing progress
  Once filled the whole machine go to the next step: injection of 2x72 bunches from SPS and nominal spacing in the LHC
  Try and reduce bunch-length to enhance scrubbing

## Slide 8: Day 8
Ramp/squeeze/collision with 50 ns beams (same number of bunches as achieved with 75 ns if compatible with vacuum). For the ramp vacuum interlock levels will be restored to nominal settings.
Criteria for the decision on operation with 75 or 50 ns:
50 ns:
  if pressures after injection of ~900 bunches with 50 ns spacing are in the range of 10-8 mbar or lower, heat loads due to e-cloud in the range of 10 mW/m/aperture or lower and limited transverse blow-up (<20 %) is observed at the injection plateau. It must be noted that the bunch intensity achievable with 50 ns is larger than with 75 ns
  If no evidence on strong dependence on energy/orbit
75 ns:
  If the above criteria are not met

## Slide 9: Impact of injection septum change in SPS
Venting of the SPS TIDVG absorber is required to replace the SPS injection septum
This might lead to outgassing when dumping the LHC beam on the dump
The extent of the phenomenon will be better known only during the pumping down after the repair and when we will start to put beam in the SPS.
We might be limited in intensity for a couple of days  Plan B to be defined with studies with no experimental magnets ON:
  RF set-up with equal voltages on B1/B2
  Test ramp
  Injection and abort gap cleaning setting-up
  Decay correction
  Snapback correction
  RF feedback optimization

## Slide 10: Measurements
  Emittance along the trains  ? + Federico
  Tune shift along the bunch train with Schottky  Tatiana + (logged?)
  Stable phase  Giulia, Walter + Elena S.
  BBQ  ?
  HeadTail monitor  Benoit?
  Heat load  Walter + Cryogenics
  Vacuum pressures  Vacuum team
  Bunch-by-bunch position  Dedicated monitor available? Who is responsible in ABP?
  Lifetime of the bunches along the train  Giulia? + ….
  What else?