## Slide 1: BE-CO work for the TS Outcome of the actions
23 – 28 Apr 2012

## Slide 2: BE/CO work (1/5)
Planned intervention on the DB service Tuesday 24th April
  8:00 – 8:15 – Restart of the ACCCON cluster in order to change the 10g compatibility mode
    ALL db accounts on the ACCCON cluster (dbabco & acc_settings) will not be available for a period of ~ 15 min.
  8:15 – 9:45 – Upgrades of the APEX repositories on ACCCON and LASERDB clusters
    All APEX-based applications running on both clusters
  8:15 – 9:00 – Upgrade of the Oracle application service running on cs-ccr-oas1
    Controls Configuration ADF Editors
=> ALL DONE. NO PROBLEMS ENCOUNTERED
Remove of the symbolic link "/user/pcrops/data -> /user/slops/data" as LSA will redeploy the SDDS_BROWSER
=> NOT DONE. POSTPONED TO NEXT TS

## Slide 3: BE/CO work (2/5)
There will be an intervention on the network Faraday cage in BA6 24 Apr 2012 all day which will impact the technical network in BA6.
  See https://indico.cern.ch/getFile.py/access?resId=0&materialId=0&confId=187026
  CANCELLED by IT/CS
New version of the DIAMON agent deployed in order to detect faster a lost agent
=> POSTPONED TO THE NEXT TechnicalStop
BE/CO/IN will try to reboot as many Linux and Windows Consoles, Vistars, CCC Wall Screens, Web Servers (CS-CCR-WWW1/3) and General Purpose Samba Servers (CS-CCR-SAMBA1/GWPC) during the week and/or Tuesday (Injector related)). This is for the usual Operating System updates.
ALMOST ALL DONE. Wall Screens, Web Servers and Samba Servers were not rebooted. NO PROBLEMS ENCOUNTERED
Cu/Cu Wfip repeater changed in RE38
=> DONE. NO PROBLEMS ENCOUNTERED

## Slide 4: BE/CO work (3/5)
Change of the ROOT password policy in the FrontEnd
  No direct root access anymore (password has been changed and will be kept secret)
  Users shall login to the FECs with their personal login, they must do a first hop to a CO trusted machine. No password is required in the FECs, authentication is based on a public/private DSA keyset
  Root privileges can be obtained using sudo, which is automatically enabled for everyone in the dscdev group. Root privileges can be restricted with a sudoers list.
=> DONE. NO PROBLEMS ENCOUNTERED
Install 24Gb of RAM in CS-CCR-COLSA (was 12Gb)
=> DONE. NO PROBLEMS ENCOUNTERED
Samba server upgraded to prevent the https://www.samba.org/samba/security/CVE-2012-1182 security hole
  Herve Milcent is announcing the upgrade to his users who may prefer certain times during the LHC Technical Stop week.
  The update can be performed in a few seconds and no reboot is required. In rare cases PVSS clients on Windows Terminal may have difficulty reconnecting.
=> DONE. NO PROBLEMS ENCOUNTERED

## Slide 5: BE/CO work (4/5)
BE/CO/HT will perform a CTR firmware upgrade intervention on the machines listed next slide.
  This has already been agreed upon with Lars Jensen. This is to solve a bug and introduce new features.
  As to the modifications this firmware introduces, there are mainly:
    1. bug fix of a potential loss of 1ms bug.
    2. fix of MEN-A20 compatibility in the VME core.
    3. support of additional HPTDC functionality.
  All the CTRs in the field were upgraded in Apr 2011 to the new version of the firmware. The ones that are quoted here were overlooked during that campaign. It is likely that those CTRs were in lab machines and silently sneaked into operation during the last year.
  The expected time per machine is about 20'. It can be done mostly concurrently, so each machine can be scheduled at a (coincident) given time. BE/CO/HT will arrange with Lars for this.
=> DONE. NO PROBLEMS ENCOUNTERED

## Slide 6: BE/CO work (5/5)
Upgrade of all CMW Proxies for LHC & Injectors
  Logging System, many client GUIs, WorkingSets
  New Proxy version was running since start-up on two instances: LHC BBQ, PS CTM. No problems were reported/observed. In case of problem, it can be quickly rolled-back to the previous version.
  We found several problems/issues in the new Proxy version after deployment for PS CTM
  All issues were understood and fixed
  New version was deployed only for: LHC BBQ, LHC BETS & PS CTM
  Now in validation mode, if all goes fine, new version will be deployed for other instances during no-beam time
  Outcome: partially DONE, to be followed-up
Upgrade of one JMS node in CO-PRO cluster
  Many systems depending on JMS (e.g. Logging, LSA, InCA, PM, …)
  New JVM setting are being tested now on other JMS instance (CMW Log). In case of problem, it can be quickly rolled-back to the previous JVM settings.
  One of brokers in the CO-PRO JMS cluster was upgraded to the new version of ActiveMQ
  Updated also JVM memory settings
  Outcome: DONE
Upgrade of CMW Configuration Server due to a fixture in data retrieval procedure
  All operational LHC front-ends.
  Service was operational during 2011 run and worked without any problems. The current change has to reflect changed db connection string and new deployment procedure.
  Service was upgraded and is working properly
  Outcome: DONE