## Schedule
|  |  | Monday 25 | [12 empty] | Night | Tuesday 26 | [12 empty] | Night | Wednesday 27 | [12 empty] | Night | Thursday 28 | [12 empty] | Night | Friday 29
|  |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
Point 1
Patrol
Cryo Maintain
Secteur 12 | LSS1R
Arc
LSS2L
Point 2
Patrol
Cryo Maintain
Secteur 23 | LSS2R
Arc
LSS3L
Point 3
Patrol
Secteur 34 | LSS3R
Arc
LSS4L
Cryo Maintain
Point 4
Patrol
Cryo Maintain
Secteur 45 | LSS4R
Arc
LSS5L
Point 5
Patrol
Secteur 56 | LSS5R
Arc
LSS6L
Cryo Maintain
Point 6
Patrol
Cryo Maintain
Secteur 67 | LSS6R
Arc
LSS7L
Point 7
Patrol
Secteur 78 | LSS7R
Arc
LSS8L
Cryo Maintain
Point 8
Patrol
Cryo Maintain
Secteur 81 | LSS8R
Ti8
Arc
LSS1L
Ouvert. Blindage
Tests de décharge dipole
56
ISRM
23
Système Evacuation
inhibé
Accès restreints pour GS-ASE des PAD suivants :
UJ43
UX451
UJ43
RP
P8
UJ83
TIM
PM85 - biometry
PZ33 lift
PM15
lift
PZ45
lift
PM56
lift
PM65lift
PZ65
lift
PM45
lift
PM76 lift
PM65 - biometry
patrol
patrol
PM65 - PAD1
PM18
lift
I
II
RP
P1
UJ16
RP
P2
UJ23
RP
P2
UJ27
RP
P4
UJ43
RP
P4
UJ47
RP
P5
UL55
RP
P5
UJ56
RP
P6
UJ63
RP
P6
UJ67
RP
P8
UJ87
RP
P1
UJ14
RP
P3
RP
P3
RP
P7
RP
P7
I
II
II
PM25 lift
RP
Ti8
PM65 - MAD
X-rays
Tests
RD1
PM85 lift
RP
P4
UX451
RP
P4
UX451
RP
P6
UP63
RP
P6
UP63
CV
CV
CV
CV
CV
X-rays
RF RECONDITIONING
RF RECONDITIONING
UJ63 - PAD & MAD
UJ67 - PAD & MAD
UP63 - PAD
VIP
patrol
PM45 - biometry
PZ45 - biometry
PM25 - PAD1
patrol
PM76 - biometry
X-rays
X-rays
X-rays
X-rays
X-rays
Tests
RD1
patrol
patrol
II
MKB
Survey - polygonale
Fermeture Blindage
Survey - Triplets 8L
Survey - Triplets 8R
Survey - Triplets 5L
Survey - Triplets 2L
RP
Ti2
Survey - Triplets 5L
Survey - Triplets 5L
Survey - Triplets 5L
Survey - Triplets 5R
Survey - Triplets 5R
Survey - Triplets 5R
Survey - Triplets 5R
WCC collar
WCC collar
WCC collar
WCC collar
WCC collar
WCC collar
WCC collar
WCC collar
I
II
II
I
II
II
I
II
II
I
II
II
I
II
II
I
II
II
VIP
I
II
I
II
patrol
patrol
PM15
lift

## Progress
Monday | Tuesday | Wednesday | Thursday | Friday